## Overview
QUANTAEDGE ¦ WEB ↔ ANDROID BEHAVIOUR DECISIONS
Choose the final behaviour page-by-page. The decision dropdown is prefilled with a recommendation; change it anywhere you prefer another outcome.
Decision summary | Count | HOW TO USE THIS WORKBOOK
Total page/behaviour decisions | 62 | 1 | Review each row in Decision Matrix: one behaviour decision per row.
New shared behaviour | 15 | 2 | Compare the current web and Android behaviours before choosing.
Combine both | 27 | 3 | Change Your decision in column I using the dropdown.
Use Web as standard | 15 | 4 | The Recommended default in column H is guidance, not a commitment.
Use Android as standard | 1 | 5 | Use Combine both when rules should match but UI may be native/responsive.
Android-only add-on | 4 | 6 | Use New shared behavior when neither existing version is adequate.
Web-only | 0 | 7 | Keep Android-only add-on for secure offline tests/pages and native scanning/photo/file actions.
Discuss | 0 | 8 | Run QA Checklist after decisions; Pass requires actual evidence, not source inspection.
Implemented on main | 62
Decision rule: Web is the default reference for content completeness and information hierarchy. Android may use native controls. Identity, permissions, grading, progress and certificate status remain backend-authoritative.
Scope: public landing → login/signup/reset → student journeys → parent journeys → certificate verification → logout/session expiry. Admin and HRMS are outside this user-facing web-vs-Android matrix.
WHY THIS WORKBOOK EXISTS
This workbook is the durable decision and progress ledger for QuantaEdge web ↔ Android UI parity. It keeps one row per page/behaviour, records the agreed target behaviour and implementation status on main, and separates code implementation from real end-to-end verification so future sessions can resume without repeating the audit.
RESUME RULE — READ THIS BEFORE CONTINUING
Green in Decision Matrix means the implementation is recorded on main; it does not mean the journey passed end-to-end testing. Start from the next incomplete item in QA Checklist, record evidence for actual browser/account/device testing, and update this workbook after changes. Never mark a QA case passed from source inspection or CI alone. Preserve backend contracts and existing behaviour; make additive changes unless a change is explicitly approved. Keep this workbook and the companion tracker note committed on main.

## Decision Matrix
PAGE-BY-PAGE DECISION MATRIX
One row = one decision. Column I is editable and prefilled with column H's recommended default.
Meaning: Use Web/Android as standard = use that platform's behaviour as shared reference; Combine both = keep the strongest parts of each; New shared behavior = define new rules where neither is sufficient.
ID | Journey | Page / screen | Behaviour to decide | Web today | Android today | Difference / gap | Recommended default | Your decision (dropdown) | Proposed behaviour if selected | Acceptance check / done when | Source URLs | Implementation status on main | Implementation record / next action
PUB-01 | Public entry | Landing / welcome | Should Android have a full public landing page before login? | Full marketing landing with learning pitch, how-it-works, subjects, parent benefits, account entry points and legal links. | Unauthenticated app opens directly into login; no equivalent full public landing flow found. | Capability gap | Combine both | Combine both | Keep the website's content hierarchy and CTA destinations; implement a native, compact Android landing screen, not a pixel copy. | Fresh install opens welcome screen; Student and Parent CTAs reach the correct login; legal links work; signed-in users are not unnecessarily sent through welcome. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PUB-02 | Public entry | Landing / brand | Which brand lockup, name, colours and tagline should be standard? | Centralized QuantaEdge brand component uses canonical icon, approved lockup, navy/orange and tagline. | Centralized native QuantaEdgeBrand renders canonical Q icon, same name, colours and tagline, with different native sizing. | Presentation difference | Combine both | Combine both | Keep one approved brand design and canonical asset; permit only size/spacing differences per screen and platform. | Landing, login, workspace header, menus and footer use the same approved logo asset/name/tagline; no mPay rebranding or legacy wordmark. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/QuantaEdgeBrand.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeBrand.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PUB-03 | Public entry | Landing / language | Which language control is available before sign-in? | Language switcher on landing and login; web UI uses Hindi/Devanagari-based Hinglish and English. | Language toggle exists on login screen; no landing screen to host it. | Capability gap | Combine both | Combine both | Expose the same Hindi/English choice on Android welcome and login. It changes interface language only, not account role or learning content preference. | Switching language updates all visible public/auth copy and preserves entered form values; Hindi is Devanagari, not phonetic Roman Hindi. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PUB-04 | Public entry | Landing / legal links | Should public privacy and terms be available from Android? | Privacy and Terms links are in public landing footer. | No equivalent public footer/landing was found in Android. | Capability gap | Use Web as standard | Use Web as standard | Keep public Privacy/Terms pages as the source of truth; link to them from the native welcome screen/footer. | Links open the intended public page and remain accessible before login; no login is required to read them. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/page.tsx | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
AUTH-01 | Authentication | Role choice / login entry | Should Student and Parent login be separate or combined? | Separate student login (/login/student) and parent login (/login). | One native login screen offers a Student/Parent choice. | UX difference | Combine both | Combine both | Keep two unmistakable role choices. Android may use a role-choice screen/switch, but the resulting forms and role isolation match web. | Both roles can start from landing; no accidental role default; back navigation returns to prior public page; credentials/session are never mixed. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/login/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/login/student/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
AUTH-02 | Authentication | Student login | What are the required fields and validation? | Parent mobile, student username, password; mobile is digit-limited to ten digits; explicit role/session response validation then full navigation. | Parent mobile, username, password fields; source does not show equivalent ten-digit formatting enforcement on native input. | Parity gap | Use Web as standard | Use Web as standard | Use web field order, constraints and error language as standard; preserve native password keyboard/autofill and server session validation. | Invalid mobile/username/password rejected consistently; successful login enters Student workspace; student cannot end up on Parent dashboard or remain on login. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/login/student/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
AUTH-03 | Authentication | Parent password login | Should parent password login behaviour match web? | Password login supported with strict PARENT role/workspace/identity checks. | Password login supported with role-specific Android workspace handling. | Mostly aligned | Combine both | Combine both | Keep the web's strict Parent session confirmation plus Android's native form/autofill interaction. | Wrong credentials show a localized message; successful login enters Parent only; Student session cannot satisfy Parent identity. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/login/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
AUTH-04 | Authentication | Parent OTP login | Should OTP remain a sign-in option? | Parent web flow supports password and OTP login, including OTP request/verify. | Native login screen shows password sign-in, signup and reset; no OTP sign-in option is exposed on the main parent login screen. | Capability gap | Use Web as standard | Use Web as standard | Add parent OTP login on Android, using the same backend OTP purposes and session validation. Keep password login too. | Existing parent without password can sign in with OTP; invalid/expired OTP is handled; successful OTP login reaches Parent dashboard only. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/login/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
AUTH-05 | Authentication | Parent signup | Should signup steps and validation be the same? | Parent signup uses mobile + OTP verification and password setup. | Android has a parent signup OTP flow. | Mostly aligned; runtime validation needed | Combine both | Combine both | Keep same purpose, required fields, password policy, confirmation, error/success messages; allow native input/keyboard treatment. | New parent account is created once; success logs in the correct account; retries do not create duplicates or leave user on an ambiguous form. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/login/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
AUTH-06 | Authentication | Forgot / reset password | Should reset require the same OTP/password flow? | Parent reset uses registered mobile, OTP and new password with validation. | Native parent reset screen uses OTP and password setup. | Mostly aligned; runtime validation needed | Combine both | Combine both | Match OTP purpose, password requirements, confirmation, localized success/error and post-reset navigation. | Correct account can reset password; wrong/expired OTP is rejected; new password works; old password behaviour matches backend policy. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/login/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
AUTH-07 | Authentication | Session / role routing | What decides the destination after login and refresh? | SessionBoundary checks role, workspace and exclusive role identity; handles refresh recovery, public-entry redirect and expired sessions. | Android verifies /auth/me, then explicitly enters parent or student home and stores encrypted cookie/session state. | Security contract | New shared behavior | New shared behavior | Define one server-authoritative session contract across clients: role + workspace + one identity; browser/native wrappers may differ but must enforce the same rules. | Test Parent, Student, expired, mixed/malformed, refresh, back, relaunch, logout and role-switch cases; no cross-workspace access. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/SessionBoundary.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
NAV-01 | Global shell | Student primary navigation | Which destinations are in the primary nav and in what order? | Five groups: Today, Learn, Practice & Tests, Progress & Certificates, Textbook Library. | Five groups: Today, Learn, Practice, Progress, Books. | Aligned contract; labels differ | Combine both | Combine both | Use exact same five destination IDs/order and semantic ownership. Labels can be short on small screens, but destination meaning must remain consistent. | Exactly five student primary destinations on both; Profile, Tests, Results, Certificates, Leaderboard, Classes, Tutor and Logout are nested/utilities. | https://github.com/Manav326/QuantaEdge/blob/main/docs/plans/web-android-route-parity-matrix.md ; https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/WorkspaceLayout.tsx | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
NAV-02 | Global shell | Parent primary navigation | Which destinations should parents get? | Three destinations: Family Report, Children's Profiles, Parent Profile. | Three parent groups: Family report, Children, Profile. | Aligned contract; UI hierarchy differs | Combine both | Combine both | Keep three role-specific destinations. Use native details/sheets where helpful; do not force student nav onto Parent. | Only Parent session can open Parent pages; three destinations remain available from portrait/landscape and appropriate account utilities. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/WorkspaceLayout.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/StudentNavigationContract.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
NAV-03 | Global shell | Portrait / landscape navigation | How should the Android nav adapt? | Responsive web: desktop sidebar and mobile bottom bar. | Android uses bottom bar in portrait and left rail in landscape, based on orientation. | Intentional platform difference | Use Android as standard | Use Android as standard | Keep web responsive layout; keep Android orientation-driven placement. Same destination order and active state, not identical geometry. | Portrait uses bottom nav even on a large portrait device; landscape uses left rail; rotating never loses answers, page, chat, or playback position. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/WorkspaceLayout.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/StudentNavigationContract.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
NAV-04 | Global shell | Header / profile / language | What belongs at the top right? | Top bar has student/parent account avatar menu and language settings. | Native header has profile photo/initial dropdown; app/content language controls are inside it. | Parity detail | Combine both | Combine both | Use approved brand left; profile/avatar and visible current app-language indicator at right. Student content-language setting remains distinct; certificate language stays in certificate flow. | Header stays consistent across every signed-in screen; selected language is evident; no duplicated/extra header and no back arrow where not needed. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/WorkspaceLayout.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
NAV-05 | Global shell | Logout placement | Where should Logout be? | Logout in web workspace sidebar footer and account menu. | Logout is in native account menu; Parent home also exposes a redundant sign-out action. | Minor UI inconsistency | Combine both | Combine both | Keep logout available in account utilities. Avoid a duplicate prominent Parent-home logout button if the global account menu is reliably accessible. | Logout available from every protected screen, clears server/native session, returns to correct role login, and Back cannot restore protected content. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/WorkspaceLayout.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
DASH-01 | Student / Today | Student home hierarchy | Which dashboard layout is the reference? | Shows curriculum completion, graded accuracy, subjects, course enrolment/progress, textbook availability, recommendations and learning entries. | Shows progress/accuracy, subject cards, quick-access rows and recommendation. More actions are repeated as rows; course catalog flow not found. | Content/layout parity gap | Use Web as standard | Use Web as standard | Use web's information hierarchy/completeness as the reference; rebuild with native components, remove duplicates, don't omit real capabilities. | Both show the same meaningful data/actions/state; empty and loading states match; no duplicate shortcut competing with primary navigation. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
DASH-02 | Student / Today | Subject cards / chapter counts | What should subject cards display? | Subject cards show chapters, published lessons, chapter PDF count and complete-book link/status. | Subject cards show completion and entry to lessons; resource catalog opens separately. | Content gap | Use Web as standard | Use Web as standard | Show common subject information: chapters, published lessons, completion, chapter PDFs and complete-book link/status when available. | Given the same account/content dataset, each subject card reports the same counts and the correct accessible book/chapter route. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
DASH-03 | Student / Today | Independent course discovery / enrolment | Should course catalogue and join flow exist on Android too? | Lists independent courses, enrols via API, then shows enrolled course progress. | Equivalent catalogue/enrolment path wasn't found in current Android navigation/home/source inspected. | Capability gap | Use Web as standard | Use Web as standard | Implement the web flow in native UI: catalogue, availability/enrolled state, join action, busy/error feedback, course progress. | Available course can be enrolled once; refresh retains enrolment; enrolled progress matches web/backend; failed enrolment gives retryable error. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/page.tsx | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
DASH-04 | Student / Today | Recommendation and next step | What should recommended next action look like? | Shows tailored learning plan/recommendation with pathway into the selected lesson/diagnostic. | Opens backend recommendation from native dashboard; rendered using native quick-action row. | Mostly aligned; presentation differs | Combine both | Combine both | Keep the same server-provided recommended item, due diagnostic logic and explanation, using native presentation on Android. | Recommendation IDs and destination are the same; tapping opens the matching lesson/diagnostic and preserves return path. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
LEARN-01 | Student / Learn | Subject and lesson list | How should subjects/topics be organized? | Web has subject/topic pages with learning structure, progress and relevant resource actions. | Android has subject selection and API-backed lesson list; native cards/controls differ. | UX difference; validate parity | Combine both | Combine both | Match content ordering, subject filter, lesson naming/status and resume/return path; Android may use native list cards. | Same published lessons appear in the same curriculum order with equivalent available/in-progress/completed status and errors. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/learn/LearnClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
LEARN-02 | Student / Learn | Lesson blocks and media | Which content sequence and rendering is authoritative? | Renders structured teaching blocks, questions and supported media inside lesson flow. | Native LessonContentBlock renders matching block types/media using Android components. | Presentation difference | Combine both | Combine both | Use one backend content sequence and authored content; web/native renderers must preserve ordering, math, examples, illustrations, captions, audio/video and text alternatives. | For the same lesson, both clients show the same blocks and questions in the same order; missing translations are explicit; media errors have retry/fallback. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/learn/LearnClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/LessonContentBlock.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
LEARN-03 | Student / Learn | Inline lesson question and feedback | What is the answer-save/correctness behaviour? | Answers save through API and UI shows saved state/feedback; question presentation can be expanded within lesson. | Native QuestionCard saves using question API and displays saved/correct/wrong/awaiting-check feedback. | Business-rule parity | New shared behavior | New shared behavior | Define one answer-state contract shared by all learning surfaces: unsaved, saving, saved, correct, incorrect, needs review, error/retry. | Saved state persists after reload; correct/wrong colours and text match; no answer marked correct without authoritative grading. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/learn/LearnClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
LEARN-04 | Student / Learn | AI Tutor | What should tutor context, modes and history do? | Contextual tutor from lesson/questions with conversation history and configured/unconfigured states. | Native tutor screen with mode controls and persisted conversation via tutor API. | Mostly aligned; verify real data | Combine both | Combine both | Keep web's visible lesson context and return path; match native implementation to same tutor APIs, history, modes, content language and feature-flag state. | Tutor answer is attached to correct lesson/question, conversation persists after navigation/reopen as specified, UI follows app language while tutor follows content language. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/learn/LearnClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/TutorScreen.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
LEARN-05 | Student / Learn | Live classes | What are the join/leave/attendance rules? | Class catalogue/filtering, server-checked join/leave and session attendance; subject filtering and pagination. | Native class catalogue and join/leave/attendance hand-off. | Mostly aligned; live test needed | New shared behavior | New shared behavior | Use same class availability, access checks, scheduled status, join/leave outcomes and server attendance. Meeting hand-off may be native-specific. | Same session list/status appears; join denied consistently where unauthorised; attendance updates after join/leave; no duplicated active attendance. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/classes/ClassesClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
LEARN-06 | Student / Learn | Recorded classes / playback | What is the playback/resume behaviour? | Video playback stores position/watched time/completed state and resumes in browser. | Native Media3 player with authenticated session, periodic server progress save and resume. | Intentional presentation difference | Combine both | Combine both | Same recording catalogue, saved position, watched duration and completion rules. Use browser player on web and protected Media3 player on Android. | Switching device/platform resumes from server state; completed/watch progress agrees; leaving player saves progress when feasible. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/classes/ClassesClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/docs/android/ANDROID_IMPLEMENTATION_PROGRESS.md | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PRAC-01 | Student / Practice | Topic practice | Should practice be one question per screen? | One question at a time, auto-save/retry/completion summary and answer feedback. | One question at a time, save/feedback/retry and completion summary. | Aligned direction; confirm states | Combine both | Combine both | Keep the single-question flow; align question type coverage, next/back policy, retries, graded vs ungraded outcomes and final summary. | Same topic/session identity and backend question set; answer remains saved after app/process restart as supported; wrong answers are visibly red and correct answers green. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/practice/PracticeClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PRAC-02 | Student / Practice | Practice question availability | What happens if no approved questions exist? | Explains that practice starts only when approved questions for the exact micro-topic are available. | Native empty state tells the learner no approved questions are available for the lesson. | Mostly aligned | New shared behavior | New shared behavior | Keep exact micro-topic/topic identity, approved-question filtering, no unrelated-question fallback and clear next action. | If 0 approved questions, both show a helpful empty state and do not create a misleading session or show questions from another topic. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/practice/PracticeClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PRAC-03 | Student / Diagnostic | Initial diagnostic | Should diagnostic follow the formal-test interaction layout? | Question/answer flow and recommendation-driven availability; page can display its own web flow. | Native diagnostic currently uses a scrolling list of questions, unlike the one-question native formal test UI. | Interaction difference | New shared behavior | New shared behavior | Decide one standard interaction. Recommended: one question per screen with progress/navigation, final submit confirmation, and server-owned diagnostic outcome; keep due-only entry rule. | Diagnostic appears only when due/available; answers save; submit persists completion; home recommendation changes based on server response; no second diagnostic if already completed. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
TEST-01 | Student / Practice & Tests | Test catalogue and filters | Which tests and controls should be shown? | Formal assessment list, subject/filters, status, attempts/results, pagination and page size. | Native assessment list, subject filter, pagination and offline-enabled test actions. | Mostly aligned; validate edge states | Combine both | Combine both | Same server-published test catalogue, role/subject access, current status, attempt eligibility, pagination semantics. Android adds offline preparation only when test permits it. | Same test IDs/status/eligibility and stable order for same filter; page size/empty/loading/error states match; hidden/unpublished tests are not exposed. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/tests/TestsClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
TEST-02 | Student / Practice & Tests | Active formal test screen | Question navigation and layout? | One question per screen, timer, numbered jump navigator, answer-save state and Previous/Next. | One question per screen, timer, answer save and Previous/Next; equivalent numbered jump navigator not found in reviewed screen. | Parity gap | Use Web as standard | Use Web as standard | Retain the web one-question panel and question-rail concept; implement native question-number navigation with clear current/answered/unanswered states. | Can jump between questions; current selection persists; timer/deadline and saved answers remain correct; rotation/reopen restores expected attempt state. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/tests/TestsClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
TEST-03 | Student / Practice & Tests | Answer autosave and retry | How should failed/ongoing answer saves be communicated? | Debounced/batched answer save, pending edits and explicit error/retry-on-submit messaging. | API-backed save and native busy/error handling; preserves the permitted offline attempt queue. | Business-rule detail | New shared behavior | New shared behavior | Use one save-state contract; keep Android offline queue as additional state. Never silently drop dirty answers. | Throttle/network failure tests confirm prior saved answer is retained, pending edit is retried, no duplicate submission and UI clearly says what has/hasn't saved. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/tests/TestsClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/docs/plans/web-android-route-parity-matrix.md | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
TEST-04 | Student / Practice & Tests | Review before submitting | Should there be a final check? | Explicit confirmation, answered/unanswered counts and warning that submitted answers can't be changed. | Native submit flow includes submit action; review counts/confirmation parity requires validation against complete screen/device path. | Needs exact E2E verification | Use Web as standard | Use Web as standard | Use web confirmation contents as baseline; implement a native dialog/sheet with answered, unanswered, keep working and submit actions. | Unanswered count matches real attempt answers; cancel returns to the active attempt unchanged; confirm submits exactly once. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/tests/TestsClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
TEST-05 | Student / Practice & Tests | Test submission / timed expiry | What is finalisation behaviour? | Flushes dirty answers, submits attempt, handles timer expiry and distinguishes released from awaiting-staff-review state. | Server-backed submit, timer-triggered submission and offline sync exception. | Security/business contract | New shared behavior | New shared behavior | Same server authoritative deadline, answer flush, submit idempotency, terminal status. Preserve Android-only authorized offline submission/sync path. | No answer submitted after deadline is silently editable; retries do not double-submit; expired test status agrees with backend; offline pending isn't shown as graded. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/tests/TestsClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
TEST-06 | Student / Results | Awaiting review | How are written answers waiting for staff described? | Explicitly says written/short/long answer responses are assigned for staff review and final score/feedback wait. | Native result/attempt state has pending/review statuses; exact matching message requires runtime verification. | Status copy difference / verify | Use Web as standard | Use Web as standard | Keep the same pending-review distinction and plain-language message. A pending attempt must not look like a final score or a failed test. | Pending test shows saved/submitted date and awaiting review; no premature score, answer key or certificate is shown; later refresh shows released review. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/tests/TestsClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
TEST-07 | Student / Results | Released test result and answer review | Which details must the result show? | Score, percentage, correct/incorrect/unanswered counts, question-by-question review, marks, feedback and explanation; certificate action where eligible. | Native result/review screens show score/question details, feedback/explanation and certificate actions in native layouts. | Mostly aligned; runtime test needed | Combine both | Combine both | Keep all authoritative data from web/backend and adopt best native layout; one question per screen for result review too. | Same released score/marks/correctness/teacher feedback/explanation and certificate status for the same attempt; answer key never shows before release. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/tests/TestsClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
TEST-08 | Student / Results | Leaderboard | Where and how is Top-20 shown? | Nested inside Tests & Results, not a primary destination. | Internal route exists under the Practice group; no sixth nav item. | Mostly aligned | Use Web as standard | Use Web as standard | Keep leaderboard nested in Tests & Results. Preserve server ranking by score/time and Top-20 limit; don't create a separate primary nav icon. | Same ranked students/marks/time/eligibility on the same data; no extra nav destination; parent doesn't get student impersonation. | https://github.com/Manav326/QuantaEdge/blob/main/docs/plans/web-android-route-parity-matrix.md | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PROG-01 | Student / Progress | Progress and mastery dashboard | Which progress metrics should appear? | Shows curriculum/subject completion, accuracy, concept mastery and recent assessments using backend metrics. | Native screen shows subject progress, practice accuracy, study time, mastery and recent results. | Content detail / align data | Combine both | Combine both | Use same server-defined metrics and meanings; choose web's hierarchy with native adaptive card layout. Avoid duplicate/conflicting client-side score calculations. | Same account/dataset yields same totals, percentages and mastery state; no rounding or alternate score rules that change certificate eligibility. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/progress/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/StudentProgressScreen.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
CERT-01 | Student / Certificates | Certificate centre and eligibility | What types are available and who is eligible? | Subject completion and qualifying released admin-created-test result; independent certificate-language selection; existing/revoked states and linked results. | Native certificate screen has subject tracks, eligible assessments, achievement type, language, issue/retrieve/verify UI. | Similar business flow; defect reported by user | New shared behavior | New shared behavior | Use one backend-driven certificate state machine and one request contract. When an existing certificate is issued, open/retrieve that certificate by the returned certificate ID; don't display a missing record. | With eligible account, issue once; refresh lists it; selecting an existing certificate opens correct ID; ineligible/revoked/pending rows explain status; no 'Certificate not found' after successful issue. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/certificates/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/StudentCertificatesScreen.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
CERT-02 | Student / Certificates | Certificate preview / PDF / PNG download | What happens after choosing a certificate and format? | Preview/download PDF or PNG; user has reported an existing-certificate flow reaching 'Certificate not found' and no download. | Native PDF/PNG save actions and FileProvider/save-location flow; user reports prior Android certificate issue remains. | Known runtime defect / verify both | New shared behavior | New shared behavior | Define a durable certificate ID→artifact retrieval contract, stable download response/content type and error mapping. Show real success only after file bytes and file save are confirmed. | Web actually downloads the selected format; Android file picker saves a valid file that opens; returned certificate ID maps to existing issued record; no silent failure, stale ID or generic false success. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/certificates/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/StudentCertificatesScreen.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
CERT-03 | Student / Certificates / Public verify | QR / barcode / manual ID verification | What is the authoritative verification outcome? | Public web verifier uses certificate ID, displays server status/details and may support camera scan where browser API exists. | Native scanner reads QR/linear barcode and calls server verification endpoint; manual ID field also exists. | Native affordance differs; reported scanner regression needs runtime QA | Combine both | Combine both | Backend status and all displayed fields are canonical; web keeps public URL/manual entry, Android keeps premium camera QR/barcode scanner; both show the same result semantics. | Test valid, revoked, malformed, unrelated, expired/missing IDs and camera denied. Android opens scanner and then displays same server status/details as web verifier. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/certificate/verify/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/StudentCertificatesScreen.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
TEXT-01 | Student / Library | Book/chapter discovery | What is the library organization? | Complete textbook/book-parts grouped by subject; chapter PDFs nested in one expandable book; pagination and language-specific catalogue. | Native resource catalogue supports subject/resource discovery and protected offline operations; exact web grouping/detail parity not established. | Layout/function parity gap | Use Web as standard | Use Web as standard | Use web hierarchy as reference: subject → complete book/book parts → chapter PDFs, with accurate language/pages and one chapter-list expansion at a time. Native cards allowed. | Same entitled documents in the same curriculum order; complete book and chapter entry points are discoverable; no unrelated language fallback is silently labelled as requested. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/textbooks/TextbooksClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
TEXT-02 | Student / Library | Secure reader controls | Which reading controls should match? | Page number entry, previous/next, zoom, fit page, fit width, thumbnails, fullscreen, keyboard shortcuts, page retry. | Native reader displays one rendered page image with previous/next and secure offline cache; no equivalent complete zoom/fit/thumbnail/fullscreen control set found in reviewed screen. | Significant UI-control gap | Use Web as standard | Use Web as standard | Implement native controls corresponding to web's reading controls wherever usable on Android. Keep server-rendered pages and no direct PDF export/print path. | Student can jump page, zoom/fit, open thumbnails, enter/exit fullscreen, retry a failed page and return to the correct origin. Access checks still apply on every protected page. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/textbooks/TextbooksClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
TEXT-03 | Student / Library | Offline textbook downloads | Should offline page copy be available? | Secure online page reader; no ordinary PDF download/print control. | Encrypted rendered page copies, resumable WorkManager downloads and local-copy deletion. | Intentional Android-only add-on | Android-only add-on | Android-only add-on | Keep this as an Android native extra. Do not expose a weaker web file-export route merely to match it. | Downloaded pages are encrypted, account-scoped, accessible offline only to authorized account; removal cancels job and deletes only local copy; source remains server-side. | https://github.com/Manav326/QuantaEdge/blob/main/docs/plans/web-android-route-parity-matrix.md ; https://github.com/Manav326/QuantaEdge/blob/main/docs/android/ANDROID_IMPLEMENTATION_PROGRESS.md | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
CLASS-01 | Student / Learn | Live/recorded class listing | Which filters and states should show? | Live/recorded tabs, subject filters, session states and pagination. | Native API-backed live/recorded class lists and subject navigation. | Mostly aligned; validate | Combine both | Combine both | Match session data, scheduled/available states, filtering, pagination, loading/error and no-recording states; native layout may differ. | Same class/recording records and current status for the same account; inaccessible session cannot be joined. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/classes/ClassesClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
CLASS-02 | Student / Learn | Meeting join / leave and attendance | How should joining a live class work? | Web joins meeting hand-off and uses server-side attendance join/leave. | Native join/leave uses current API and meeting hand-off. | Server business contract | New shared behavior | New shared behavior | Same authorization and attendance transitions; platform may choose browser/installed-app hand-off appropriate for device. | Join denied consistently without authorization; leave updates attendance once; navigation/backgrounding doesn't silently leave duplicate active attendance. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/classes/ClassesClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/docs/android/ANDROID_IMPLEMENTATION_PROGRESS.md | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PARENT-01 | Parent / Family report | Family dashboard and child selection | Which report content should be standard? | Family report with child switching, report metrics, recent learning/test/certificate details. | Native child list and native report screen; layouts are simpler/different. | Content hierarchy difference | Use Web as standard | Use Web as standard | Use web's report information hierarchy; Android presents the same records in native components and preserves child selection. | All authorized children selectable; report content changes to selected child only; metrics/results/certificates match backend; no student-session impersonation. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/parent/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PARENT-02 | Parent / Children | Create child profile | Which fields and consent should be required? | Name, class, learning language, username/password, subject tracks and guardian-consent confirmation. | Native child-create screen supports name/class, credentials, tracks and consent; existing implementation notes profile language support may be narrower. | Field/policy parity to validate | Combine both | Combine both | Use the backend-supported fields, validations, consent wording and student-credential policy. Never offer an unsupported child-account language option. | Same required fields and validation; profile created once; child can sign in; parent account sees the child and access settings immediately refresh. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/parent/children/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/ParentChildCreateScreen.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PARENT-03 | Parent / Children | Edit child profile | Can parent edit name/class/language? | Editable child display name, class and learning language; class promotion policy preserves historic progress. | Native management form has credentials, tracks and archive but not equivalent profile editing fields in the screen inspected. | Capability gap | Use Web as standard | Use Web as standard | Add the same editable profile fields in Android, respecting supported language values and allowed class-promotion transition only. | Saved name/class/language persists across refresh and login; historic progress/attempts remain attached; invalid grade transitions are rejected consistently. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/parent/children/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/ParentChildManageScreen.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PARENT-04 | Parent / Children | Child credentials and subject tracks | What can parent change? | Update username/password and enabled Maths/Science subjects with API feedback. | Native child-management screen has username/password changes and subject toggles. | Mostly aligned | Combine both | Combine both | Match constraints and successful-save feedback; keep password masked and never echo the stored password. Same active-track permission rules. | Changes persist after refresh; username uniqueness and password policy enforced by server; disallowed last-track removal rejected; only selected subjects show to student. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/parent/children/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/ParentChildManageScreen.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PARENT-05 | Parent / Children | Archive / restore child | Should archived profile recovery exist on Android? | Can archive child, view archived profiles, restore after fresh guardian consent; asks to set student credentials again for security. | Native management screen supports archive with confirmation; archived list/restore flow not found in the routes/screens inspected. | Capability gap | Use Web as standard | Use Web as standard | Implement archived list, restore confirmation and fresh consent; require credentials to be set again. Retain learning history per backend rules. | Archived profile isn't treated as active; restore requires consent; old credentials aren't silently reused; history survives and parent/child access follows server policy. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/parent/children/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/ParentChildManageScreen.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
PARENT-06 | Parent / Profile | Parent profile and photo | Which profile information and save behaviour should match? | Detailed profile form: photo upload/remove, name/email, read-only mobile/user ID, city/state, occupation/organisation, preferred language. | Native profile screen has editable profile fields and photo-picker save/remove hooks; exact field parity and language-save coupling need validation. | Field/behaviour parity gap | Combine both | Combine both | Match web field set, validation, help text and save results; Android uses system Photo Picker and native image handling. Preferred learning language must not silently mutate App Language. | Photo survives app restart; remove returns neutral placeholder; profile save refreshes header; app language only changes when explicitly changed from app-language control. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/parent/profile/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/ParentProfileScreen.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
STU-01 | Student / Profile | Student profile and photo | What fields and photo behaviour should be common? | Profile form includes photo, identity, personal/school information, learning preferences and account eligibility/lifecycle actions. | Native form supports profile fields/photo and learning-language change; lifecycle workflow parity not found in inspected native profile screen. | Capability gap / field parity | Combine both | Combine both | Match web's supported profile data and eligibility actions; keep Android Photo Picker/native resizing. Use same neutral placeholder and true-save feedback. | Save/remove photo verified against server; fields round-trip after refresh; role/eligibility lifecycle only exposes actions allowed by server. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/profile/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/StudentProfileScreen.kt ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/ProfilePhotoPickerInput.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
LANG-01 | Global / all pages | App-interface language | Which strings change when App Language changes? | LanguageProvider covers Hindi/English UI, persists preference and keeps UI/content language independent. | Native app language preference and bilingual Compose strings; hardcoded or Hindi-only strings may remain in some feature/error screens. | Translation coverage gap | New shared behavior | New shared behavior | Define the shared localization contract and audit all visible strings; platform translation keys/resources may differ but meaning/coverage must match. | Switch each screen Hindi↔English without losing work; no untranslated hardcoded errors/buttons except intentional source-authored content. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/LanguageProvider.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/AndroidLocalization.kt | Done — code on main | Commits 631312b + 266e79f: localized remaining fixed role/login/legal/textbook labels; added bilingual resources and a CI audit for direct Compose Text literals. Real browser/device E2E remains separate.
LANG-02 | Global / student flows | Learning-content language | What determines lesson/question/book/tutor language? | Separate learning language preference, persisted locally and through student language API. | Separate content-language setting and server persistence in native flow. | Preference contract; coverage to test | New shared behavior | New shared behavior | Selected content language must govern content/question/practice/tutor/resource requests, independently of UI and certificate language. | Run Hindi UI+English content and English UI+Hindi content cases on lesson/practice/tutor/books/tests; missing translation is explicit, never mislabelled fallback. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/LanguageProvider.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/docs/plans/web-android-route-parity-matrix.md | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
LANG-03 | Global / certificate flows | Certificate language | Should certificate language be independent? | Separate persisted certificate-language preference used by certificate generation/preview. | Separate native certificate-language preference used in issue request. | Aligned contract; test | Combine both | Combine both | Keep certificate language independent of UI and learning content on both clients. | All four UI/content language combinations can issue the chosen certificate language; toggling it does not change other preferences or current question/page. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/LanguageProvider.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
SESS-01 | Security / all protected flows | Session timeout and resume | What is the agreed inactivity and absolute-expiry rule? | Refresh recovery exists; current SessionBoundary heartbeat logic checks recent activity; source inspection cannot prove final server expiration policy. | Encrypted native cookie jar plus a narrowly allow-listed recovery snapshot; actual server expiry/session recovery requires device/backend verification. | Security contract; E2E required | New shared behavior | New shared behavior | Specify one server-side absolute expiry and inactivity rule; implement each platform using its secure storage/navigation model. Respect explicit logout/revocation. | Test idle intervals, backgrounding, browser back, app kill/relaunch, access-token expiry and refresh-token expiry; agree behaviour and error/redirect across platforms. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/SessionBoundary.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/data/SecureCookieJar.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
SESS-02 | Security / logout | Explicit logout | What should logout clear and where should it return? | Posts server logout and routes to role-specific login; fetch refresh is excluded on logout. | Posts logout, clears native session/profile/offline-owner state and goes to native login. | Mostly aligned; test data boundaries | New shared behavior | New shared behavior | Same server revocation and post-logout guarantee. Clear only the correct role's active session and sensitive session-local state; preserve allowed non-sensitive learning records on server. | After logout, protected API calls fail; Back cannot reopen dashboard; re-login requires authentication; local protected session caches are inaccessible. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/WorkspaceLayout.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/QuantaEdgeApp.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
NATIVE-01 | Android-only extension | Offline formal assessments | Should web have an equivalent offline mode? | Web assessed flows are online and server-backed. | Android has specifically permitted encrypted offline attempts, WorkManager sync and server-authoritative grading. | Intentional platform-only feature | Android-only add-on | Android-only add-on | Retain Android offline assessment as an add-on rather than forcing identical offline implementation in browser. Offline sync is only for explicitly permitted tests. | Offline attempt can resume, encrypted answers sync only through authorized workflow, server grades/releases; ordinary generated tests stay online-only. | https://github.com/Manav326/QuantaEdge/blob/main/docs/plans/web-android-route-parity-matrix.md ; https://github.com/Manav326/QuantaEdge/blob/main/docs/android/ANDROID_IMPLEMENTATION_PROGRESS.md | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
NATIVE-02 | Android-only extension | Camera scanner | Should scanner be added to web as well? | Public verifier accepts manual certificate ID and may use browser BarcodeDetector/camera depending on support. | Native app contains premium QR/barcode scanner path; user reported the scanner failed to open in current builds. | Native enhancement; regression reported | Android-only add-on | Android-only add-on | Keep Android native QR/barcode scanner. Web may keep browser-supported camera scan as optional enhancement, not a blocker for core parity. | Scanner opens with permission handling, detects supported QR/barcodes, calls same verify endpoint and renders same status/details as manual lookup. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/certificate/verify/page.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/StudentCertificatesScreen.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
NATIVE-03 | Android-only extension | Native save/share and protected document controls | Should native file handling remain? | Browser uses web preview/download behaviour and secure page renderer without a PDF export/print path. | Android uses native save location for issued certificate artifacts and protected offline document management. | Intentional platform difference | Android-only add-on | Android-only add-on | Keep native file-save/chooser and permitted certificate save/share; do not introduce PDF export on protected textbook reader solely for UI parity. | PDF/PNG bytes are valid and reflect the same certificate; protected textbook pages remain protected and account-scoped. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/student/textbooks/TextbooksClient.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/StudentCertificatesScreen.kt | Done — code on main | Implementation is recorded in docs/plans/web-android-ui-parity-implementation.md; real-account/device E2E remains separate.
UI-01 | Global / all pages | Loading, empty, error and success states | Should these states have matching meaning and action? | Web uses explicit loading, error/retry and empty messages in many pages; specific pages may have gaps. | Android uses native progress/error/empty components; some messages remain Hindi-first or differently worded. | State-contract gap | New shared behavior | New shared behavior | Define standard state meanings and recovery actions. Wording localized separately but equivalent; success only after actual save/server acknowledgement. | For every API-backed page, cover loading, empty, permission denied, expired session, recoverable network failure, retry and successful save. | https://github.com/Manav326/QuantaEdge/blob/main/apps/web/app/components/LanguageProvider.tsx ; https://github.com/Manav326/QuantaEdge/blob/main/apps/android/app/src/main/java/com/quantaedge/android/ui/AndroidLocalization.kt | Done — code on main | Commits c94b622, ef59f6b and f5aa098: shared Android loading/error state; HTTP 401 sign-in recovery and 403 permission-denied messaging; safe read-only retry; course/textbook fetch failure vs true-empty states; archived profile, progress, diagnostic and results loading/error states. CI run 38765080366 passed. Real-account/browser/device E2E remains pending.

## Shared Standards
SHARED STANDARDS — APPLY ACROSS EVERY PAGE
Product-wide rules to preserve unless a decision explicitly changes them.
ID | Standard | Rule | Type
STD-01 | Product reference | Web defines content completeness and information hierarchy by default; Android uses native presentation unless decision says otherwise. | Shared standard
STD-02 | Brand | Use same approved QuantaEdge logo asset, name, navy/orange palette and tagline; adapt only sizing/spacing. | Required
STD-03 | Student navigation | Exactly five primary groups, same order: Today, Learn, Practice & Tests, Progress & Certificates, Textbook Library. | Required
STD-04 | Parent navigation | Exactly three destinations: Family Report, Children’s Profiles, Parent Profile. | Required
STD-05 | Identity/security | Server-authoritative role + workspace + identity; student and parent sessions distinct and never interchangeable. | Required
STD-06 | UI language | App language changes interface strings only; Hindi UI copy uses Devanagari-based Hinglish conventions. | Required
STD-07 | Learning language | Selected learning-content language controls lesson/question/practice/tutor/resource requests; never silently mislabel fallback content. | Required
STD-08 | Certificate language | Certificate language is independent of UI and learning content language. | Required
STD-09 | Correctness | Correct = green, incorrect = red, pending/ungraded = neutral; use text/icons in addition to colour. | Required
STD-10 | Data ownership | Progress, grading, eligibility, certificate status and child permissions remain backend-authoritative. | Required
STD-11 | State handling | All data-backed pages need loading, empty, recoverable error/retry, permission denied, stale session and success handling. | Required
STD-12 | Return paths | Return to originating lesson, test/result, document or selected-child report; do not reset valid in-progress work. | Required
STD-13 | Android navigation placement | Portrait bottom nav; landscape left rail, with same destinations and order. | Native standard
STD-14 | Android-only additions | Preserve encrypted offline tests/resources, native camera scanner, Photo Picker and native save/share as secure native additions. | Native standard
STD-15 | Evidence | A source code match is not a passed real-device E2E test. Mark QA pass only after test evidence/logs are recorded. | Required

## QA Checklist
END-TO-END QA CHECKLIST
Update the Status dropdown only after running the case. Pass requires actual browser/device/backend evidence.
Test ID | Journey | Page / scenario | Expected outcome | Status | Evidence / notes
E2E-01 | Public landing | Fresh install / signed-out open | Welcome screen renders, both role CTAs work, language and legal links are available. | Not started
E2E-02 | Student authentication | Student login success/failure | Correct validation and destination; no stuck login and no Parent session. | Not started
E2E-03 | Parent authentication | Parent login with password and OTP | Both methods work; role/workspace confirmed before Parent dashboard. | Not started
E2E-04 | Authentication | Signup and password reset | OTP purpose, password validation, retries and final account/session state correct. | Not started
E2E-05 | Security | Role separation / direct URLs | Student cannot open Parent pages and Parent cannot open student learning/test attempts. | Not started
E2E-06 | Session | Refresh, back, reload and expiry | Correct workspace restored or routed to login; protected data not shown after expiry/logout. | Not started
E2E-07 | Today | Dashboard / recommendations | Same progress values and recommendation for same account/content; CTA opens expected target. | Not started
E2E-08 | Courses | Catalogue / enrolment | Enrolment persists after refresh and course progress is consistent. | Not started
E2E-09 | Learning | Subject → topic → lesson | Same published sequence/content and return path. | Not started
E2E-10 | Learning | Inline question / tutor | Answers persist; UI/content language separation; contextual tutor follows correct lesson/question. | Not started
E2E-11 | Practice | One-question practice and completion | Same approved question set, correct/wrong feedback, retry and summary state. | Not started
E2E-12 | Diagnostic | Due / not due / completed | Visibility, saved answers and completion/next recommendation agree. | Not started
E2E-13 | Formal tests | Take test / question navigation | Timer, question rail, saved answers and rotation/reopen states work. | Not started
E2E-14 | Formal tests | Submit and pending review | Confirmation counts accurate; no double submission; pending answers don't appear final. | Not started
E2E-15 | Results | Released answer review | Marks, score, correctness, teacher feedback and explanation agree. | Not started
E2E-16 | Certificates | Issue existing/new certificate | Existing IDs resolve; issue creates downloadable artifact; no 'not found' after success. | Not started
E2E-17 | Certificates | PDF and PNG output | Both formats open; branding, recipient, language and verification code agree. | Not started
E2E-18 | Verification | Web manual ID / Android scanner | Valid, revoked, invalid and missing certificate statuses and data agree. | Not started
E2E-19 | Textbooks | Find book/chapter and open reader | Language matches selected content language; correct document/page opens. | Not started
E2E-20 | Textbooks | Reader controls and retry | Page jump, zoom/fit, thumbnails, fullscreen, error/retry and return path work. | Not started
E2E-21 | Android offline | Download/read/remove resource | Encrypted per-account copies work offline; removal deletes only local copy. | Not started
E2E-22 | Classes | Join/leave and attendance | Access checked and attendance recorded once; recorded playback resumes and saves progress. | Not started
E2E-23 | Parent | Create child and set credentials | Consent, fields, username/password and child login work end-to-end. | Not started
E2E-24 | Parent | Edit, archive and restore child | Profile changes persist; restore needs fresh consent and new credentials; history retained. | Not started
E2E-25 | Parent | Family report and child certificates | Selection scopes all displayed metrics/certificates to chosen child. | Not started
E2E-26 | Profile | Profile fields and photo | Save/remove, header update, fallback avatar and refresh persistence work. | Not started
E2E-27 | Language | UI/content/certificate language matrix | All four UI/content combinations plus independent certificate language pass. | Not started
E2E-28 | Responsive | Web desktop/mobile and Android portrait/landscape | Controls remain visible, labels fit, orientation changes do not discard work. | Not started
E2E-29 | Logout | Student/Parent logout | Server session revoked, protected back-navigation blocked, new sign-in required. | Not started
E2E-30 | Accessibility | Keyboard, screen reader and text scaling | Core actions accessible; focus, touch targets, contrast and larger Devanagari text work. | Not started